## day0
Day 0 – Planning & Design
Key Activities | General Planning
Requirements gathering (capacity, coverage, use cases: voice, video, BYOD, IoT). | Define use cases (e.g., office, warehouse, voice, video, IoT).
RF design and predictive site surveys (Ekahau, Hamina, etc.). | Determine client density (for high-density designs, plan ≤ 25 clients/AP).
SSID strategy (user, guest, IoT segmentation). | Perform predictive and/or on-site RF surveys (Ekahau/Hamina).
Authentication/AAA architecture (802.1X, RADIUS, SAML). | Plan dual 5 GHz radio configurations (e.g., MR57 with dual 5 GHz radios).
IP addressing/subnetting design (DHCP scopes, IP per SSID/VLAN). | Plan PoE budgeting (per switch stack and IDF).
Integration planning (identity, logging/SIEM, NAC, MDM, location analytics). | Plan VLANs and subnets per SSID (avoid broadcast domains >500 clients).
High Availability planning (dual uplinks, RF overlap). | Define SSID strategy (user, guest, IoT, voice).
Cloud dashboard setup: | Design for roaming requirements (fast roaming, L2 vs L3).
Organization & Network hierarchy.
Licensing and inventory management. | Special Topics from Docs
Role-Based Access Control (RBAC) setup. | Enable client load balancing in high-density settings.
Apply band steering and disable 2.4 GHz where applicable.
NetOps Ansible Automation Opportunities | Use L3 roaming with centralized NAT for seamless handoff across subnets.
Inventory import via API | Plan Voice VLANs, WMM, and DSCP to preserve QoS for VoIP (e.g., Webex).
Organization/network structure setup | Define RF Profiles per environment (open vs high-interference areas).
License assignment
Network configuration templates

## day1
Day 1: Deployment & Initial Configuration
Key Activities | Physical Deployment
Physical installation of APs based on RF design. | Install APs based on survey results (ceiling height, spacing, AP models).
Device claiming and tagging in the Meraki dashboard. | Use low-gain omnidirectional antennas unless scenario requires otherwise.
Template-based configuration: | Connect APs to PoE switches and validate link speeds (1GbE or higher).
SSIDs, VLANs, authentication, firewall rules.
RF profiles (channel planning, TX power, band steering). | Meraki Dashboard Config
Test user onboarding & Wi-Fi connectivity validation. | Claim APs and tag by site/location.
Captive portal/guest access configuration if needed. | Configure:
VPN or traffic tunneling configuration (if using Meraki AutoVPN). | SSIDs (with segmentation, PSK/802.1X)
RF Profiles
NetOps Ansible Automation Opportunities | L3 roaming settings (centralized NAT or with anchors)
AP bulk provisioning (claiming, tagging, naming) | QoS profiles (DSCP tagging, WMM support for VoIP)
Template assignment to networks/devices | Traffic shaping for critical applications
SSID & RF profile configuration at scale | Enable Air Marshal (WIPS) and rogue AP containment.
SSID enable/disable for specific time periods or zones | Conduct on-site validation:
Device group policy enforcement | Coverage, roaming, authentication, voice/video performance

## day2
Day 2 – Operations, Monitoring & Optimization
Key Activities | Monitoring
Monitoring: | Use Wireless Health, Client Timeline, and RF Spectrum analytics.
AP/client health dashboards | Monitor roaming events (especially if using L3 roaming).
Channel utilization and interference | Validate voice/video performance using QoS dashboards and packet loss.
Rogue AP detection & alerts | Optimization
Optimization: | Adjust RF Profiles based on real-world interference and usage.
Dynamic RF adjustments (or manual tuning) | Split SSID load across bands or APs to reduce contention.
Adjustments to SSID load balancing, minimum bitrate settings | Optimize minimum bitrate (e.g., start at 12 Mbps or higher in dense areas).
Security: | Enable DFS channels if needed.
Firmware upgrades | Security & Management
WPA3 rollout, segmentation enforcement | Firmware upgrades (staggered across sites).
Guest traffic isolation | Review and update rogue AP policies.
Change management: | Review location analytics and telemetry.
Adding new APs or sites
Adjusting RF or network profiles
Analytics/Reporting:
Usage reports
Application performance
Client behavior/location tracking
NetOps Ansible Automation Opportunities | Ansible Automation Targets
Scheduled firmware upgrades | SSID updates (password rotation, enable/disable guest)
API-driven anomaly detection reports | RF Profile adjustments (TX power, channel width)
Backup/export of configuration (for compliance) | Scheduled firmware updates
Auto-remediation (e.g., disable SSID if rogue traffic exceeds threshold) | Compliance snapshot exports (config audit)
Automated client policy assignments | L3 roaming profile assignment
VLAN/SSID tuning for congestion or interference
Email/SIEM alert integration (via API/webhooks)

## cwdp
Define Specifications for the WLAN |  | Design the WLAN |  | Deploy the WLAN |  | Validate and Optimize the WLAN
Collect business requirements and constraints |  | Define WLAN architectures and select the appropriate architecture for a design |  | Ensure proper understanding and implementation of the design |  | Confirm the WLAN system is operational
| Business use cases and justification |  | Controller-based (physical and virtual) architectures |  | Implementation meeting |  | AP Status
| User requirements |  | Distributed (cloud-based and local WNMS) |  | Explain design decisions to implementers |  | Verify PoE provisioning of power requirements are met
| Regulatory compliance |  | Standalone/Autonomous APs |  | Ensure understanding of design deployment | Perform an RF validation survey
| Industry compliance |  | Dynamic vs. static channel assignment |  | Distribute required documentation |  | Ensure coverage requirements
| Budget |  | Dynamic radio management | Recommend or perform essential deployment tasks |  |  | Evaluate impacts of contention and interference
| Aesthetics |  | Software defined radios |  | Understand and perform installation procedures for different WLAN architectures | Perform client performance testing
| Architectural constraints |  | RF profiles |  | (cloud-based, controller-based, WNMS, autonomous) |  | Connectivity testing
| Mounting restrictions |  | Select and/or recommend the appropriate equipment for the design and selected |  | Infrastructure configuration supporting the WLAN (DHCP, DNS, NTP, switches, and |  | Application testing
| Access restrictions |  | architecture (APs, antennas, controllers, managed services) |  | routers) |  | Roaming testing
| Time constraints | Produce a design to meet requirements |  |  | Channel assignment, automatic radio management, and transmit power |  | Capacity testing
| Building codes and safety codes | Select and use the appropriate design tools |  |  | configuration |  | Security testing
Collect and define technical requirements |  |  | Design and survey software and hardware |  | Installation procedures for cloud-based APs, controller-based APs, WNMS APs, and | Recommend appropriate physical adjustments
| Vendor selection |  | Spectrum analysis software and hardware |  | autonomous APs |  | AP
| Location services such as RTLS |  | Access points and antennas | Perform an installation audit for quality assurance |  |  | Antenna and connectors
| Latency requirements |  | Portable power source |  | Verify proper AP and antenna location and orientation | Recommend appropriate RF adjustments
| Signal strength requirements |  | Tripods |  | Verify aesthetic requirements are met |  | RF channel assignment
| Capacity requirements |  | Measuring tools |  | Verify physical security of the installation |  | RF channel bandwidth
| Security requirements |  | Cameras |  |  |  | RF coverage (transmit power, radio count, antennas)
| BYOD and guest access |  | Personal Protective Equipment (PPE) |  |  |  | RF interference issues
| Roaming | Select and use the appropriate design methodologies |  |  |  | Recommend remediation for application issues
| Monitoring |  | WLAN predictive design (new builds/site or area not accessible) |  |  |  | Connectivity issues
| Authentication and encryption |  | Validated RF modeling |  |  |  | Application issues
| Applications and their specific requirements |  | AP-on-a-Stick (APoS) measurements |  |  |  | Roaming issues
| WLAN upgrade requirements, when applicable |  | Bridge and mesh planning |  |  |  | Capacity issues
| Bridge link requirements, when applicable | Understand and use the common features of wireless design software |  |  |  |  | Security issues
| Voice over WLAN (VoWLAN), when applicable |  | Import and scale floor plans |  |  | Implement knowledge transfer and hand-off
| Client devices including most important and least capable device |  | Model attenuation of the site (including calibration) |  |  |  | System training
| Requirement areas |  | Select and place APs and antennas |  |  |  | Solution documentation and assets
Collect project documentation |  |  | Adjust AP and antenna settings |  |  |  | Validation documentation
| Validated floor plans |  | Define requirement areas and parameters |  |  |  | Digital or physical assets
| Network infrastructure |  | Define channel and power settings |  |  |  | Guides
| Network diagrams | Select and use common vendor features and make configuration recommendations |  |  |  |  | Floorplans
| AP locations |  | Band steering |  |  |  | Configuration documents
| Existing network services including DNS, DHCP, NTP, and authentication |  | Automatic/static channel selection |  |  |  | Final meeting (Q&A and hand-off)
| servers |  | Load balancing
| Switch capabilities and capacity |  | RF/AP templates
| Cabling infrastructure | Design for different client and application types
| Cabling maps and plans |  | VoIP handsets
| Wiring closet locations |  | Laptops
| Power availability and PoE capabilities |  | Handheld scanners
| Existing wireless systems |  | Smartphones and tablets
| Previous design/survey documentation |  | IoT and smart devices
Define requirement areas including essential metrics for each requirement |  |  | Location tracking systems
| Client device types and capabilities |  | Voice and video systems
| Applications and their requirements | Ensure end-to-end QoS is properly implemented
| User and device density |  | WMM
| SSIDs |  | Wired and wireless QoS mappings
| Security settings |  | QoS markings, classifications, and queues
| Understand common vertical markets | Define and recommend security solutions
Gather information on environmental factors |  |  | Monitoring (detection and prevention)
| Building materials |  | Authentication servers
| Attenuation values |  | EAP methods
| Ceiling heights |  | Authentication types
| Site annotations (photos, notes, plans) |  | Encryption types
| Wireless environment scan | Design for secure roaming
| Packet captures |  | Secure BSS transition (roaming)
| Spectrum captures |  | Vendor roaming solutions
| Wi-Fi scanners |  | Client support issues
Create, distributed, and communicate design documentation
Bill of Materials (BoM)
Design reports
Physical installation guide
Source: Wireless design methology adapted from, Certified Wireless Design Professional (CWDP)